## Sheet1
CS 470 Artificial Intelligence - Term Project Activities Log
Name: | Montana Merkle | Project: | Performance Recommendation System For Soccer Players
Date | Time | Hours | Task
2024-10-07 | 13:00 | 1 | Studied the administrator view of TITAN database
2024-10-17 | 12:00 | 2 | Gathered TITAN data for all players for all games and removed trackers with unreasonable speed (from being on while in the car)
2024-10-17 | 14:00 | 4 | Selected which metrics to use and finalized TITAN data set to be used (only use game sessions)
2024-10-17 | 18:00 | 1 | Looked at past class programs to determine which technique I wanted to use to cluster data
2024-10-21 | 14:00 | 1.5 | Researched/Decided which common exercises I wanted the decision tree program to predict from (since these exercises would be practiced by past players for sure)
2024-10-21 | 15:30 | 2 | Questioned past players (whose data is on the TITAN database) on what exercises they did to improve and if it worked (Y/N) in preparation for decision tree program
2024-10-22 | 15:15 | 2 | Adjusted the mean shift algorithm in class example to cluster player from the data file, but not enough clusters so modified past Kmeans++ algorithm
2024-10-22 | 17:15 | 1.5 | Looked into the best way to count how many times each player is in each cluster (since many entries per player) to determine which cluster they actually belonged to
2024-10-31 | 13:00 | 4 | Finalized clustering program (provided clean output and groupings of players to each cluster)
2024-11-02 | 11:30 | 2 | Create TITAN data set for past players to start on the decision tree
2024-11-02 | 13:30 | 2.5 | Start on decision tree program using previous players data set
2024-11-03 | 11:00 | 1 | Modify the decision tree program to use a random forest classifier instead to see if that improves accuracy (it did not.)
2024-11-03 | 12:00 | 1 | Research how to improve the accuracy of the model since small data set
2024-11-08 | 16:00 | 1 | Created a data set of previous players that included both games and practices to see if a larger data set would improve accuracy of model
2024-11-08 | 17:00 | 0.5 | Tested random forest and decision tree classifier with the previous player's game data and all sessions data. Recorded findings
2024-11-08 | 17:30 | 2 | Modified the clustering program to find the average of all the clusters, tested program by finding average of clusters manually in excel to ensure correct
2024-11-08 | 19:30 | 1 | Integrated both the random forest program and clustering program together to predict the class of each cluster based on its average
2024-11-11 | 16:00 | 3 | Created rough base for GUI using tkinter
2024-11-11 | 19:00 | 2 | Integrated prior program into the GUI program
2024-11-14 | 14:00 | 2 | Tested to ensure file and user action validation are working
2024-11-14 | 16:00 | 2 | Worked on the aesthetics of the GUI
2024-11-14 | 18:00 | 2 | Tested the program using a fake game data CSV file to ensure program can be used with other files
2024-11-15 | 13:00 | 1.5 | Wrote the instructions to run the program and configured the final code zip file
2024-11-16 | 11:00 | 3 | Worked on the final paper for the project
2024-11-16 | 16:00 | 2 | Worked on documenting and tracing all the code found from references to the implimentation in the code fo the "what I did and didn't do" section of the final paper
2024-11-18 | 18:00 | 1.5 | Worked on the final presentation for the project
2024-11-19 | 11:00 | 2 | Finalized the final presentation for the project
Total Hours: |  | 51